## Slide 1: Project Life Cycle
PROMAR
A00 Project Management Framework
A00-02 Project Life Cycle
Notes: 2025 © delaware (general)
2025 © delaware - For internal use only (for training and guidelines)
2025 © delaware - Confidential (for commercial proposals to customers)

## Slide 2: project life cycle
DISCOVER
EXPLORE
DEPLOY
INITIATE
EXECUTE
RUN
Pre-project
Business Blueprint (BBP)
Fit-to-Standard (F2S)
Conceptual Design (CCD)
Customer Process Discovery (DCY)
Hypercare (HYP)
Go Live
Final Preparation (FPP)
Preparation
Initial planning
Operate
Business Readiness Testing (BRT)
Realization (REA)
System Integration Testing (SIT)
Notes: slide_Lifecycle_01b

## Slide 4: stages and phase in the project life cycle
Project stages are subdivided into phases to organize the project into distinct periods. The project progresses through subdivided stages, each containing phases that delineate distinct periods.
These phases serve as intervals for managing the project's advancement. Quality gates are commonly established between these phases to ensure a controlled and formal transition.
It's crucial that the previous phase is closed, validated, and approved by the customer before preparing for and commencing the subsequent phase.
QG
QG
QG
QG
QG
QG
QG
The project life cycle typically consists of several stages that a project goes through from initiation to completion.
The PROMAR Project Life Cycle includes five main stages: Initiate, Explore, Execute, Deploy, and Close, with an overarching process of Monitor & Control that spans the entire project duration.
Stages
Phases
Notes: Ref_Lifecycle_01

## Slide 5: Why using Quality Gates?
Clarity and Focus | Everyone understands what success looks like from the start, helping the team stay aligned and focused.
Progress Tracking | Criteria are used in steering committees to monitor progress, timelines, and detect issues early.
Formal Closure | At the end of the phase, the same criteria confirm whether all conditions are met for official closure.
Billing Milestones | In fixed-price projects, meeting these criteria often triggers invoicing, making them both a quality and financial checkpoint.
Notes: Slide_A07Quality_08b

## Slide 6: project phases
Monitor and Control
Inception
Customer Process Discovery (CPD)
Foster a mutual understanding between the customer and consultants about the details and value of the customer’s operational processes. Create a Business Process Master List (BPML).
Conceptual Design (CCD)
Discuss and decide on core topics and issues that have a major impact on the course of the project, the scope of the blueprint and the final solution..
Fit-to-Standard / Blueprint
Fit-to-Standard (F2S)
Perform a fit/gap analysis to validate the solution functionality included in the project scope and to confirm that the business requirements can be satisfied by the standard solution.
Blueprint (BBP)
Describe company's business processes and their requirements. Define the components to be implemented and developed and build an initial product backlog (WBS).
F2S/BBP
Inception
Explore
Realization (REA)
Focus on building the new solution, e.g., configuration, custom developments, integration, data migration… but also train the key users to use and test the new solution.
System Integration Testing (SIT)
Scenario-driven testing of integrated processes starting with simple happy flows, progressing to complex and exceptional flows with full set of migrated data.
Business Readiness Testing (BRT)
End users are involved in the execution of scenario-driven test scenarios to validate the readiness of the solution from an end-user perspective.
Realization
BRT
SIT
Execute
Operate
After a period of hypercare, the customer takes over the solution
Operate
Run
Preparation
Collect and review all project info and agreements to understand and clarify the project context, objectives, scope, budget and all other agreements
Initial plan
Prepare for the effective start of the project. Elaborate project plan, governance structure, templates and tools, staffing and conduct a kick-off meeting
Plan
Prep
Initiate
Final Preparation
Complete the golive of the project, including end user training, data migration and preparation of a cutover plan
Go live
Execute the cutover plan and move from a project-oriented, pre-production environment to a live production operation.
Final Prep
Go Live
Deploy
Pre-project
The prior collaborative work by the customer and delaware with the end goal of reaching an agreement for undertaking the project (aka pre-sales phase)
Pre-Project
Discover
Notes: slide_Lifecycle_03

## Slide 7: project phases
Operate
Run
Plan
Prep
Initiate
Pre-project
The prior collaborative work by the customer and delaware with the end goal of reaching an agreement for undertaking the project (aka pre-sales phase)
Pre-Project
Discover
F2S/BBP
Inception
Explore
Realization
BRT
SIT
Execute
Final Prep
Go Live
Deploy
Notes: slide_Lifecycle_03

## Slide 8: project phases
Preparation
Collect and review all project info and agreements to understand and clarify the project context, objectives, scope, budget and all other agreements
Initial plan
Prepare for the effective start of the project. Elaborate project plan, governance structure, templates and tools, staffing and conduct a kick-off meeting
Plan
Prep
Initiate
Pre-Project
Discover
Operate
Run
F2S/BBP
Inception
Explore
Realization
BRT
SIT
Execute
Final Prep
Go Live
Deploy
Notes: slide_Lifecycle_03

## Slide 9: project phases
Inception
Customer Process Discovery (CPD)
Foster a mutual understanding between the customer and consultants about the details and value of the customer’s operational processes. Create a Business Process Master List (BPML).
Conceptual Design (CCD)
Discuss and decide on core topics and issues that have a major impact on the course of the project, the scope of the blueprint and the final solution..
Fit-to-Standard / Blueprint
Fit-to-Standard (F2S)
Perform a fit/gap analysis to validate the solution functionality included in the project scope and to confirm that the business requirements can be satisfied by the standard solution.
Blueprint (BBP)
Describe company's business processes and their requirements. Define the components to be implemented and developed and build an initial product backlog (WBS).
F2S/BBP
Inception
Explore
Operate
Run
Realization
BRT
SIT
Execute
Final Prep
Go Live
Deploy
Pre-Project
Discover
Plan
Prep
Initiate
Notes: slide_Lifecycle_03

## Slide 10: project phases
Realization (REA)
Focus on building the new solution, e.g., configuration, custom developments, integration, data migration… but also train the key users to use and test the new solution.
System Integration Testing (SIT)
Scenario-driven testing of integrated processes starting with simple happy flows, progressing to complex and exceptional flows with full set of migrated data.
Business Readiness Testing (BRT)
End users are involved in the execution of scenario-driven test scenarios to validate the readiness of the solution from an end-user perspective.
Realization
BRT
SIT
Execute
Operate
Run
Final Prep
Go Live
Deploy
Pre-Project
Discover
Plan
Prep
Initiate
F2S/BBP
Inception
Explore
Notes: slide_Lifecycle_03

## Slide 11: project phases
Operate
Run
Final Preparation
Complete the golive of the project, including end user training, data migration and preparation of a cutover plan
Go live
Execute the cutover plan and move from a project-oriented, pre-production environment to a live production operation.
Final Prep
Go Live
Deploy
Pre-Project
Discover
Plan
Prep
Initiate
F2S/BBP
Inception
Explore
Realization
BRT
SIT
Execute
Notes: slide_Lifecycle_03

## Slide 12: project phases
Operate
After a period of hypercare, the customer takes over the solution
Operate
Run
Pre-Project
Discover
Plan
Prep
Initiate
F2S/BBP
Inception
Explore
Realization
BRT
SIT
Execute
Final Prep
Go Live
Deploy
Notes: slide_Lifecycle_03

## Slide 13: project phases
Operate
Run
Monitor and Control
Pre-Project
Discover
Plan
Prep
Initiate
F2S/BBP
Inception
Explore
Realization
BRT
SIT
Execute
Final Prep
Go Live
Deploy
Notes: slide_Lifecycle_03

## Slide 14: project phases
Monitor and Control
Inception
Customer Process Discovery (CPD)
Foster a mutual understanding between the customer and consultants about the details and value of the customer’s operational processes. Create a Business Process Master List (BPML).
Conceptual Design (CCD)
Discuss and decide on core topics and issues that have a major impact on the course of the project, the scope of the blueprint and the final solution..
Fit-to-Standard / Blueprint
Fit-to-Standard (F2S)
Perform a fit/gap analysis to validate the solution functionality included in the project scope and to confirm that the business requirements can be satisfied by the standard solution.
Blueprint (BBP)
Describe company's business processes and their requirements. Define the components to be implemented and developed and build an initial product backlog (WBS).
F2S/BBP
Inception
Explore
Realization (REA)
Focus on building the new solution, e.g., configuration, custom developments, integration, data migration… but also train the key users to use and test the new solution.
System Integration Testing (SIT)
Scenario-driven testing of integrated processes starting with simple happy flows, progressing to complex and exceptional flows with full set of migrated data.
Business Readiness Testing (BRT)
End users are involved in the execution of scenario-driven test scenarios to validate the readiness of the solution from an end-user perspective.
Realization
BRT
SIT
Execute
Operate
After a period of hypercare, the customer takes over the solution
Operate
Run
Preparation
Collect and review all project info and agreements to understand and clarify the project context, objectives, scope, budget and all other agreements
Initial plan
Prepare for the effective start of the project. Elaborate project plan, governance structure, templates and tools, staffing and conduct a kick-off meeting
Plan
Prep
Initiate
Final Preparation
Complete the golive of the project, including end user training, data migration and preparation of a cutover plan
Go live
Execute the cutover plan and move from a project-oriented, pre-production environment to a live production operation.
Final Prep
Go Live
Deploy
Pre-project
The prior collaborative work by the customer and delaware with the end goal of reaching an agreement for undertaking the project (aka pre-sales phase)
Pre-Project
Discover
Notes: slide_Lifecycle_03

## Slide 15: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Monitor and Control
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Notes: slide_Lifecycle_04

## Slide 16: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Go Live
Monitor and Control
Notes: slide_Lifecycle_04

## Slide 17: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Monitor and Control
Notes: slide_Lifecycle_04

## Slide 18: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Monitor and Control
Notes: slide_Lifecycle_04

## Slide 19: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Monitor and Control
Notes: slide_Lifecycle_04

## Slide 20: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Prioritized Project Backlog
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Monitor and Control
Notes: slide_Lifecycle_04

## Slide 21: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Monitor and Control
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Notes: slide_Lifecycle_04

## Slide 22: project life cycle
Solution (technically) built
Ready for integration testing
Iterative and incremental build
in sprints of 3 to 6 weeks (all sprints of same length)
REA
Build of the solution in sprints (detailed design, build, test, show & tell and release)
Monitor and Control
Project approach
Project plan
Kick-off meeting
PLAN
Establish program or project governance and draw up initial plans​
Contract
PRE-SALES
Phase to understand project or program objectives, solution roadmap and high- level requirements​
Must
Should
Would
Could
Prioritized Blueprint Backlog
Must
Should
Would
Could
Prioritized Project Backlog
Blueprint document
Fit-gap list
BPML and backlog for realization
Scope baseline
Conceptual design
BPML and backlog for blueprint
DISCOVERY
CONC. DESIGN
Gain knowledge of the customer's business process, make key decisions to steer the project in the right direction and draw up the Business Process Master List (BPML)
F2S / BBP
Facilitate Fit-to-Standard (F2S) or blueprint (BBP) workshops to design the final solution, and define scope and backlog for REA
Tested solution
Go/No-go
SIT & BRT
Execute System Integration
Testing, Business Readiness Testing (aka User Acceptance Testing) and End-2-end testing, test data migrations (TM), test integrations and prepare for production cutover
Test Migration
1
Test Migration
2
SIT
1
SIT
2
UAT
Test Migration
3
Project closing
Hyper-care
Run & Accelerate
KIR
Keep IT Running; handover to operations or sustain support
GOLIVE
Cutover to production and hypercare
Cutover
Final
Prep
Cut-over
FPREP
Prepare Go live and start production cutover
Go Live
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Run
Explore
Execute
Deploy
Initiate
Discover
Transition to support organization
Notes: slide_Lifecycle_04

## Slide 23: outcomes
Deploy
At the end of the Deploy phase, the business is ready to start using the solutions. They have validated the processes, and the organization has been trained in the new system. The affected sites are ready with any new equipment or processes. The go-live happens!
Run
The Go live and hypercare are closed. The operation and support of the system is now transferred to the support organization.
Execute
At the end of the Execute phase, you will have an integrated solution that is built to meet the defined scope. You will have undergone system integration testing, and data migration loads. In addition, the teams are ready to execute training and change activity to prepare the organization for the upcoming deployments.
Explore
A completed confirmation of the scope, and a high-level design that provide the necessary clarity around the detailed configuration and build activity that must be undertaken, including data transformation, and organizational change impacts.
Initiate
Mobilize the project team and establish project governance and ways of working. This phase also ensured that the scope has been decomposed, and the Explore phase is ready to go.
The project team and business are aware of how the next phase will be conducted and what the expectations are for them.
Pre-project
Determine the business value, benefits and project scope to plan the project in detail with achievable and clear outcomes.
Outcome
Outcome
Outcome
Outcome
Outcome
Outcome
Monitor and Control
Run
Explore
Execute
Deploy
Initiate
Discover
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Notes: slide_Lifecycle_06

## Slide 24: key activities
Preparation
Onboard team members effectively
Establish project governance structure, roles and processes
Setup project procedures and tools
Draft strategies for OCM, data migration, integrations,...
Initiate risk register
Define organizational change and communication plan
Initial plan
Build project plan
Prepare for next phase
Schedule workshops
Guide the team on the project approach, project reporting and acceptance criteria
Kick-off meeting
Startup
Initiate project staffing
Obtain signed SOW or contract
Prepare for next phase
Handover from presales team to project team, including verbal and informal agreements and promises
Understand and clarify the project context and objectives
Review scope, budget and timeline
Customer Process Discovery
Gain knowledge of the customer's specific business processes.
Develop a Business Process Master List (BPML)
Conceptual design
Facilitate conceptual design sessions aimed at making initial key decisions and assumptions to narrow the blueprint scope
Fit-to-standard
Conduct Fit-to-Standard workshops
Blueprint
Conduct blueprint sessions
Evaluate dependencies, cross-domain and with other projects
Prepare for next phase
Review scope, budget and timeline (if applicable, agree on SOW for next phases)
Build project backlog (WBS), outlining business processes and custom developments with their delivery schedule
Develop sprint planning with sprint objectives, detailed tasks, assignments and effort allocation
Explain and schedule sprint ceremonies
Kick-off for REA
Realization
Conduct detailed design workshops
Build solution via sprint approach
Ensure alignment in domain-specific and cross-domain meetings
Perform configuration, development, and unit testing
Conduct Functional Integration Testing (FIT) and Extended FIT
Update configuration documentation
Facilitate sprint planning, standup meetings, and sprint reviews
Effectively manage change requests
Initiate detailed cutover/roll-out plan
Conduct sprint retrospective session
Prepare for next phase
Prepare test system with test data
List and write out test scripts
Check testers readiness and training
Organize and plan for SIT and BRT, ensuring smooth execution, defect resolution, and progress reporting
System integration testing
Execute SIT testing
Resolve bugs and other defects identified
Monitor defects through a dashboard and organize triage sessions
Develop of end-user documentation and training materials
Validate authorizations and security
Dry-run data migration
Dry-run cutover
Business readiness testing
Execute SIT BRT/UAT testing
Assist end-users in executing the BRT/UAT testing
Prepare for next phase
Go/No Go decision
Final preparation
Conclude end-user training sessions
Finalize cutover plan
Identify golden orders
Execute final data migration processes
Perform first tasks outlined in cutover plan
Go/No Go for Go live
Go live
Execute cutover to production environment
Monitor golden orders and KPIs
Hypercare
Engage in hypercare support activities
Prepare for next phase
Plan for operational support post-Go live
Keep It Running (KIR)
Monitor KPIs
Handover to support organization
Perform lessons learned
Harvest all files and doc
Project closing and acceptance
Evaluate future scope for next releases
Celebrate Go live with team and customer
Offboard project team
Monitor and Control
Run
Explore
Execute
Deploy
Initiate
Discover
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Notes: slide_Lifecycle_08

## Slide 25: key deliverables
Preparation
Governance structure and meeting calendar
Strategies for OCM, Data Migration, Integration,…
Risk register
Change Request template and process
Deliverables list and acceptance criteria
GDPR requirements
Welcome pack
Initial plan
High level planning with milestones and critical path
Prepare for next phase
Workshop planning
Backlog (WBS) for BBP
Project kick-off for project and BBP
Pre-project
Initial budget, and timeline
High level scope and requirements
Rate table
Application landscape
Signed SOW or contract
Safeguarded presales files and information
Prepare for next phase
Customer Process Discovery
Business Process Master List (BPML)
Conceptual design
Conceptual design
Key decisions and assumptions refining the blueprint scope
Fit-to-standard
List of gaps
Blueprint
Signed-off blueprint documents
Identified (scope) changes
List of required custom developments
Prepare for next phase
Backlog (WBS) and initial sprint planning for REA
Release procedure and calendar
Kick-off for REA
Realization
Completed solution build
Configuration documentation
Specs for custom developments
Trained Business Process Owners (BPOs) and key users
Initial version of cutover plan
Prepare for next phase
Go /No Go for SIT and BRT
Set up test system and test data
Test plan for SIT and BRT
Repository of test cases for each business scenario
Test scripts written for all test cases
Kick-off for SIT/BRT
System integration testing
Executed test cases
Resolution of bugs and other defects identified
Solution fully tested in quality environment
Signed-off SIT report and Go/No Go for BRT/UAT
Business readiness testing
End-user documentation and training material
Signed-off BRT/UAT report
Prepare for next phase
Go /No Go for final prep
Final cutover plan
Cutover practicalities and communication plan
End-user training plan
Final preparation
End-user training
Migrated data
Final business readiness checks
Go /No Go for Go live
Go live
Final production cutover
Prepare for next phase
Operational support after Go live (AMS)
Keep It Running (KIR)
Lessons learned
Project closing and acceptance document
Monitor and Control
Run
Explore
Execute
Deploy
Initiate
Discover
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
Notes: slide_Lifecycle_07

## Slide 26: Quality Gates - example
Monitor and Control
Run
Explore
Execute
Deploy
Initiate
Discover
Customer Process Discovery validated
Conceptual design validated
Approach for the REA phase confirmed
Solution landscape validated
Blueprint documents signed off
All custom developments have been identified, prioritized, and decisions made on in-scope or out-of-scope items.
Backlog prepared for the REA phase
Sprint planning completed
SOW and budget for the REA phase finalized
REA Kick-off meeting conducted
Project management plan validated
Resource reservations approved
Project scope reviewed
High-level planning with milestones agreed
Scope agreed for the Inception and Conceptual Design phase
Approach for the BBP phase validated
Workshops planned for next phases
Project Kick-off meeting conducted
All developments validated the key-user
FIT and XFIT testing are expected to cover 90% (tbd) of the project scope.
85% (tbd) of FIT and XFIT testing executed
Fewer than 100 (tbd) open bugs remain, with a maximum of 10 (tbd) bugs per domain
No critical open bugs open
Approach for SIT phase validated
Test plans and scripts prepared
Data migration achieved 80% (tbd) accuracy
Authorizations and security finalized
Test environment and test data are in place
Testers have been trained on using the solution, performing tests, and reporting bugs.
SIT/BRT Kick-off meeting conducted
90% of SIT tests executed in each domain
Pass rate > 90%
No critical bugs open
Cutover plan prepared
90% of BRT tests executed in each domain
Pass rate > 90%
No critical bugs open
Cutover plan tested
Rehearsal run of data migration completed successfully
End-users have been trained
Production system is ready
Support for golive and hypercare organized and available
Risk mitigation actions implemented
All post-cutover tasks performed
All critical and high bugs are closed
All medium and low bugs are documented and handed over to operational support
Hypercare has been concluded, and transitions to operations has been performed
Project team is off-boarded
Project Closure document signed
Signed MSA
Signed SOW
Resource reservations
Handover to project team done
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live & Hypercare
QG
QG
QG
QG
QG
QG
QG
QG
Notes: slide_Lifecycle_10

## Slide 27: Project Playbook
INITIATE
Preparation
Quality Gate – definition
Contact List
Project Charter
Project Mgmt Plan
Deliverable Tracker
Project Governance – Basic
Project Governance - Extended
RACI matrix
Communication Plan
Project Standards
Change Request
Workstreams
High-level WBS
Project Timeline
Project Budget Baseline
Detailed Resource Plan
Team Onboarding
Risk Register
Customer Discovery Tool
Project Workbook
Supporting Tools
dlw Experience Monitor
Status Report
SteerCo
EPR
DISCOVER
Pre-project
Sales Playbook
Proposal Budget
Stakeholder Register
Opening Form
RACI matrix
Project Rate Card
MSA
SOW
Project Staffing
Handover
Software Partners
Change Onboard Session
Think-Plan-Act
Monitor and Control
Explore
Execute
Deploy
Initiate
Discover
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Go Live & Hyp.
EXECUTE
Realization (REA)
Quality Gate – definition
Hybrid Implementation Process – concept
Hybrid Implementation Process – ceremonies
Backlog for REA
Sprint Planning
Testing during REA
Documentation Standards
Internal REA Kick-off meeting
REA Kick-off meeting
Quality Gate – closing
EXECUTE
SIT & BRT
Quality Gate – definition
Testing Strategy
Testing Tools
Test Planning
Test Execution and Reporting
Defect management
Training Plan
Quality Gate – closing
DEPLOY
Final preparation
Quality Gate – definition
Final Preparation Kick-off
GoLive Readiness
Organize Hypercare and Transition
Prepare Project Closing
Lessons Learned
Documentation Archiving and Harvesting
Project Closing
Quality Gate – closing
MONITOR & CONTROL
Record Keeping
Manage Governance
Manage Contract
Manage Change Requests
Manage Scope
Manage Time
Manage Budget
Manage Quality
Manage Risk
Manage Communication
Manage Testing
Manage Workbook
EXPLORE
Inception
Quality Gate – definition
Customer Process Discovery (CPD)
Customer Process Discovery workshops – plan
Conceptual Design (CCD)
Conceptual Design workshops – plan
Business Process Master List (BPML)
Backlog for BBP phase
EXPLORE
Blueprint (BBP)
Fit-to-standard (F2S)
Fit-to-Standard workshops – plan
Blueprint (BBP)
Blueprint workshops - plan
Standards for BBP documents
Internal BBP Kick-off meeting
BBP Kick-off meeting
Sign-off and updated baselines and plans
Stakeholder Mgmt
Change Impact Analysis
Change & Communication Plan
Quality Gate – closing
Initial Plan
Workshop Planner
SteerCo and other governance bodies
Project Kick-off
Quality Gate – closing
Monitor & Control
Monitor & Control
Notes: slide_Lifecycle_09

## Slide 28: thank you for your time
Wim Vanhauwaert
wim.vanhauwaert@delaware.pro

## Slide 30: project phases
Final Prep
Realization
Plan
Prep
Pre-Project
Blueprint
Inception
BRT
SIT
Operate
Go Live
Run
Explore
Execute
Deploy
Initiate
Discover
Final Prep
Realization
Blueprint
Inception
BRT
SIT
Operate
Go Live
Pre-Project
Prep
Plan
Notes: slide_Lifecycle_03